## Tasks
Elyana | Jiahao | Shantanu |  | EVERYONE
Srikar | Lance | Yiting
Goals: |  |  |  | Towards a simplified TCL6 generator
- Simplify the TCL6 generator to a numerically simple integral consisisting of only a few unique tensors, in order to investigate higher order phenomena in open quantum systems |  |  |  | Phase 1 (Jan) | Phase 2 (first two weeks of Feb) | Phase 3 (end of Feb +Mar) | Phase 4 (April)
- Find patterns in terms that simplify expressions and enable generalization to higher order generators
Divide and Conquer Phase: Choose 9th Term - Line 13 in REDUCED NONZERO TERMS:
Formalize the Hadamard, Matrix-Product, and Unitary Evolution algebras, and DECOMPOSITION of GTxy into basis {1,sigx,sigy,sigz}; then express Line 13 in terms of the basis, and produce the list of functions to be doubly integrated. This should be done by hand and symbolically.
Tasks
To do | In Progress | Done | Date completed | Relevant Results | Notes/Comments
|  | make general timeline for TCL6 Progress | 2023-01-24 | See above
|  | Make group task list document | 2023-01-24 | Having some issues with Onedrive syncing locally
|  | Send papers to group slack | 2023-01-30
Make Shared Document for final expressions
Send reminder about the goals for the next two weeks
| Analytic Computation BY HAND of Line 13, before meeting on mid May | Calculate unitary time evolution of spin-boson system operator | 2023-05-11
| Symbolic Computation of LINE 13, based on what we learn by hand. | Write spectral density in Pauli matrix basis | 2023-05-13
| Symbolic Computation of ALL LINES | Algorithm-ize hadamard algebra in pauli basis | 2023-05-13
CODING |  | Wrote Matlab code to transform any 2x2 matrix in terms of Bloch vector | 2023-05-07 | All those code are used in processing line 13 and eventually all terms automatically
Use the same technique calculating the Hadmard Product to calculate the commutators |  | Wrote code that calculate commutator of 2x2 matrix following operation table in the basis of Pauli matrices | 2023-05-07
|  | Wrote code that calculate Hadmard Product of 2x2 matrix following operation table in the basis of Pauli matrices | 2023-05-07 | have only done hadamard products of traceless matrices --- still need to check result
| Tried to work out vector expression for matrix commutator of hadamard products | Using symbolic matlab and string to calculate all the Hadmard Product in line 13. Have the function that fill the implicit multiplication operator back into the expression ready. | 2023-06-09
|  | Debugging errors from curent code. Completed Hadmard Product terms | 2023-06-14
Preliminaries
Ramp-up
Divide and Conquer
Recombine, Unify, and Simplify
Biweekly check-ins and group troubleshooting

## Nonzero Terms
Correlation term\\\term of origin (-[0, *] omitted) | Integral Transformations |  |  | total sum | Notes
<02><14><35> | +(0t1)(013)(312)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(034)(435)(0t1)(032) | [1,2][3,4]5p
<02><14><53> | +(0t1)(013)(312)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(034)(435)(0t1)(032) | -[1,2][3,4]p5 | only a change of indices/conjugation from the previous?
<02><41><35> | +(0t1)(013)(312)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(034)(435)(0t1)(032) | -[1,2]5p[3,4]
<02><41><53> | +(0t1)(013)(312)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(034)(435)(0t1)(032) | [1,2]p5[3,4]
<02><15><34> | +(0t1)(014)(413)(012)(045) | -(0t1)(013)(035)(034)(032) | +(0t3)(035)(3t1)(054)(032) | [1,2]([3,45p]-5[3,4p])
<02><15><43> | +(0t1)(014)(413)(012)(045) | -(0t1)(013)(035)(034)(032) | +(0t3)(035)(3t1)(054)(032) | -[1,2][3,5]p4
<02><51><34> | +(0t1)(014)(413)(012)(045) | -(0t1)(013)(035)(034)(032) | +(0t3)(035)(3t1)(054)(032) | -[1,2]4p[3,5]
<02><51><43> | +(0t1)(014)(413)(012)(045) | -(0t1)(013)(035)(034)(032) | +(0t3)(035)(3t1)(054)(032) | [1,2]([3,p54]-[3,p4]5)
<03><14><25> | +(0t2)(024)(2t1)(423)(045) |  |  | -3[1,[2,4]5p]-[1,[34,2]5p]-[2,3]5[1,4p]
<03><14><52> | +(0t2)(024)(2t1)(423)(045) |  |  | 3[1,[2,4]p5]-[1,[2,34]p5]+[2,3][1,4p]5
<03><41><25> | +(0t2)(024)(2t1)(423)(045) |  |  | -[1,[2,3]5]p4-[1,3]5p[2,4]
<03><41><52> | +(0t2)(024)(2t1)(423)(045) |  |  | [1,3]p5[2,4]+[1,[2,3]p54]-[2,3][1,p4]5
<03><15><24> | +(0t2)(025)(2t1)(023)(524) | -(0t1)(014)(412)(043)(045) |  | [1,[2,3]4]5p+[1,3][2,45p]-[1,3]5[2,4p]
<03><15><42> | +(0t2)(025)(2t1)(023)(524) | -(0t1)(014)(412)(043)(045) |  | 3[1,[2,5]p4]-[1,[2,35]p4]+[2,3][1,5p]4
<03><51><24> | +(0t2)(025)(2t1)(023)(524) | -(0t1)(014)(412)(043)(045) |  | -[1,3]4p[2,5]-[1,[2,3]4]p5
<03><51><42> | +(0t2)(025)(2t1)(023)(524) | -(0t1)(014)(412)(043)(045) |  | -3[1,[2,p54]]-[1,3][2,p4]5-[2,3][1,p5]4+[1,[2,3p54]]
<04><12><35> | +(0t2)(023)(035)(2t1)(034) | -(0t2)(025)(2t1)(523)(054) |  | -[3,4]5[1,2p]+[1,2[3,4]5p]
<04><12><53> | +(0t2)(023)(035)(2t1)(034) | -(0t2)(025)(2t1)(523)(054) |  | [3,4][1,2p]5-[1,2[3,4]p5]
<04><21><35> | +(0t2)(023)(035)(2t1)(034) | -(0t2)(025)(2t1)(523)(054) |  | -[1,[3,4]5]p2
<04><21><53> | +(0t2)(023)(035)(2t1)(034) | -(0t2)(025)(2t1)(523)(054) |  | -[3,4][1,p2]5+[1,[3,4]p52]
<04><13><25> | +(0t2)(023)(2t1)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(035)(3t1)(032)(054) | -4[1,[2,3]5p]+[1,[2,34]5p]-[2,4]5[1,3p]
<04><13><52> | +(0t2)(023)(2t1)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(035)(3t1)(032)(054) | 4[1,[2,3]p5]-[1,[2,34]p5]+[2,4][1,3p]5
<04><31><25> | +(0t2)(023)(2t1)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(035)(3t1)(032)(054) | -[1,[2,4]5]p3-[1,4]5p[2,3]
<04><31><52> | +(0t2)(023)(2t1)(035)(034) | -(0t1)(015)(513)(012)(054) | +(0t3)(035)(3t1)(032)(054) | [1,4]p5[2,3]+[1,[2,4]p53]-[2,4][1,p3]5
<04><15><23> | +(0t1)(013)(312)(035)(034) | -(0t2)(025)(523)(2t1)(054) |  | -[1,4]5[2,3p]+4[2,3[1,5p]]-4[1,[2,35p]]-[2,34[1,5p]]+[1,[2,345p]]
<04><15><32> | +(0t1)(013)(312)(035)(034) | -(0t2)(025)(523)(2t1)(054) |  | 4[1,[2,5]p3]+[2,4][1,5p]3-[1,[2,45]p3]
<04><51><23> | +(0t1)(013)(312)(035)(034) | -(0t2)(025)(523)(2t1)(054) |  | 4[1,3p[2,5]]-4[2,3[1,p5]]+[1,4[2,3p]5]+[2,34[1,p5]]-[1,[2,34p5]]
<04><51><32> | +(0t1)(013)(312)(035)(034) | -(0t2)(025)(523)(2t1)(054) |  | -[1,4][2,p3]5-[2,4][1,p5]3-4[1,[2,p53]]+[1,[2,4p53]]
<05><12><34> | +(0t2)(024)(2t1)(423)(045) |  |  | 5[3,4[1,2p]]-[1,25[3,4p]]+[1,2[3,45p]]-[3,45[1,2p]]
<05><12><43> | +(0t2)(024)(2t1)(423)(045) |  |  | [3,5][1,2p]4-[1,2[3,5]p4]
<05><21><34> | +(0t2)(024)(2t1)(423)(045) |  |  | -[1,[34,5]]p2+[1,[4,5]p32]-[4,5][1,p2]3
<05><21><43> | +(0t2)(024)(2t1)(423)(045) |  |  | -[3,5][1,p2]4+[1,[3,5]p42]
<05><13><24> | +(0t1)(014)(413)(012)(045) | -(0t3)(034)(3t1)(032)(045) |  | -5[1,[2,3]4p]+5[2,4[1,3p]]-[1,35[2,4p]]-[2,45[1,3p]]+[1,[2,345p]]
<05><13><42> | +(0t1)(014)(413)(012)(045) | -(0t3)(034)(3t1)(032)(045) |  | 5[1,[2,3]p4]+[2,5][1,3p]4-[1,[2,35]p4]
<05><31><24> | +(0t1)(014)(413)(012)(045) | -(0t3)(034)(3t1)(032)(045) |  | 5[1,4p[2,3]]-5[2,4[1,p3]]+[1,5[2,4p]3]+[2,45[1,p3]]-[1,[2,45p3]]
<05><31><42> | +(0t1)(014)(413)(012)(045) | -(0t3)(034)(3t1)(032)(045) |  | [1,5]p4[2,3]+[1,[2,5]p43]-[2,5][1,p3]4
<05><14><23> | +(0t2)(024)(2t1)(423)(045) |  |  | 5[1,4[2,3p]]+5[2,3[1,4p]]-5[1,[2,34p]]-[1,45[2,3p]]-[2,35[1,4p]]+[1,[2,345p]]
<05><14><32> | +(0t2)(024)(2t1)(423)(045) |  |  | 5[1,[2,4]p3]+[2,5][1,4p]3-[1,[2,45]p3]
<05><41><23> | +(0t2)(024)(2t1)(423)(045) |  |  | 5[1,3p[2,4]]-5[2,3[1,p4]]+[1,5[2,3p]4]+[2,35[1,p4]]-[1,[2,35p4]]
<05><41><32> | +(0t2)(024)(2t1)(423)(045) |  |  | -[1,5][2,p3]4+[5,2][1,p4]3-5[1,[2,p43]]+[1,[2,5p43]]
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One group of similar terms

## cumulative correlation terms
Correlation term\\\term of origin (-[0, *] omitted) | PLLPLLPLLP | PLLPLLLLP | PLLLLPLLP | sum so far (VERIFIED from B+C+D to E) |  | PLLLLLLP | VERIFIED (from G to H) | total sum
<01><23><45> | 1[2,3[4,5p]]+1[4,5[2,3p]] | -1[2,3[4,5p]] | -1[2,3[4,5p]]-1[4,5[2,3p]] | -1[2,3[4,5p]] |  | 12345p + -1345p2 + -1235p4 + 135p42 | 1[2,3[4,5p]] | 0
<01><23><54> | -1[2,3[4,p5]]-1[4,[2,3p]5] | 1[2,3[4,p5]] | 1[2,3[4,p5]]+1[4,[2,3p]5] | 1[2,3[4,p5]] |  | -1234p5 + 134p52 + 123p54 + -13p542 | -1[2,3[4,p5]] | 0
<01><32><45> | -1[2,[4,5p]3]-1[4,5[2,p3]] | 1[2,[4,5p]3] | 1[2,[4,5p]3]+1[4,5[2,p3]] | 1[2,[4,5p]3] |  | -1245p3 + 145p32 + 125p43 + -15p432 | -1[2,[4,5p]3] | 0
<01><32><54> | 1[2,[4,p5]3]+1[4,[2,p3]5] | -1[2,[4,p5]3] | -1[2,[4,p5]3]-1[4,[2,p3]5] | -1[2,[4,p5]3] |  | 124p53 + -14p532 + -12p543 + 1p5432 | 1[2,[4,p5]3] | 0
<01><24><35> | 1[2,4[3,5p]]+1[3,5[2,4p]] | -1[2,[3,45p]] | -1[2,4[3,5p]]-1[3,5[2,4p]] | -1[2,[3,45p]] |  | 12345p + -1345p2 + -1245p3 + 145p32 | 1[2,[3,45p]] | 0
<01><24><53> | -1[2,4[3,p5]]-1[3,[2,4p]5] | 1[2,[3,4p5]] | 1[2,4[3,p5]]+1[3,[2,4p]5] | 1[2,[3,4p5]] |  | -1234p5 + 134p52 + 124p53 + -14p532 | -1[2,[3,4p5]] | 0
<01><42><35> | -1[2,[3,5p]4]-1[3,5[2,p4]] | 1[2,[3,5p4]] | 1[2,[3,5p]4]+1[3,5[2,p4]] | 1[2,[3,5p4]] |  | -1235p4 + 135p42 + 125p43 + -15p432 | -1[2,[3,5p4]] | 0
<01><42><53> | 1[2,[3,p5]4]+1[3,[2,p4]5] | -1[2,[3,p54]] | -1[2,[3,p5]4]-1[3,[2,p4]5] | -1[2,[3,p54]] |  | 123p54 + -13p542 + -12p543 + 1p5432 | 1[2,[3,p54]] | 0
<01><25><34> | 1[2,5[3,4p]]+1[3,4[2,5p]] | -1[2,[3,45p]] | -1[2,5[3,4p]]-1[3,4[2,5p]] | -1[2,[3,45p]] |  | 12345p + -1345p2 + -1245p3 + 145p32 | 1[2,[3,45p]] | 0
<01><25><43> | -1[2,5[3,p4]]-1[3,[2,5p]4] | 1[2,[3,5p4]] | 1[2,5[3,p4]]+1[3,[2,5p]4] | 1[2,[3,5p4]] |  | -1235p4 + 135p42 + 125p43 + -15p432 | -1[2,[3,5p4]] | 0
<01><52><34> | -1[2,[3,4p]5]-1[3,4[2,p5]] | 1[2,[3,4p5]] | 1[2,[3,4p]5]+1[3,4[2,p5]] | 1[2,[3,4p5]] |  | -1234p5 + 134p52 + 124p53 + -14p532 | -1[2,[3,4p5]] | 0
<01><52><43> | 1[2,[3,p4]5]+1[3,[2,p5]4] | -1[2,[3,p54]] | -1[2,[3,p4]5]-1[3,[2,p5]4] | -1[2,[3,p54]] |  | 123p54 + -13p542 + -12p543 + 1p5432 | 1[2,[3,p54]] | 0
<02><13><45> | 2[1,3[4,5p]]+2[4,5[1,3p]] | -2[1,3[4,5p]] | -[1,23[4,5p]]-2[4,5[1,3p]] | -[1,23[4,5p]] | -[1,23[4,5p]] | 12345p + -2345p1 + -1235p4 + 235p41 | [1,23[4,5p]] | 0
<02><13><54> | -2[1,3[4,p5]]-2[4,[1,3p]5] | 2[1,3[4,p5]] | [1,23[4,p5]]+2[4,[1,3p]5] | [1,23[4,p5]] | +[1,23[4,p5]] | -1234p5 + 234p51 + 123p54 + -23p541 | -[1,23[4,p5]] | 0
<02><31><45> | -2[1,[4,5p]3]-2[4,5[1,p3]] | 2[1,[4,5p]3] | [1,2[4,5p]3]+2[4,5[1,p3]] | [1,2[4,5p]3] | +[1,2[4,5p]3] | -1245p3 + 245p31 + 125p43 + -25p431 | -[1,2[4,5p]3] | 0
<02><31><54> | 2[1,[4,p5]3]+2[4,[1,p3]5] | -2[1,[4,p5]3] | -[1,2[4,p5]3]-2[4,[1,p3]5] | -[1,2[4,p5]3] | -[1,2[4,p5]3] | 124p53 + -24p531 + -12p543 + 2p5431 | [1,2[4,p5]3] | 0
<02><14><35> | 2[1,4[3,5p]]+2[3,5[1,4p]] | -2[1,[3,45p]] | -[1,24[3,5p]]-2[3,5[1,4p]] | -2[1,[3,4]5p]-[1,24[3,5p]] | 2(+[1,4[3,5p]]-[1,[3,45p]])-[1,24[3,5p]] | 12345p + -2345p1 + -1245p3 + 245p31 | [1,2[3,45p]] | [1,2][3,4]5p
<02><14><53> | -2[1,4[3,p5]]-2[3,[1,4p]5] | 2[1,[3,4p5]] | [1,24[3,p5]]+2[3,[1,4p]5] | 2[1,[3,4]p5]+[1,24[3,p5]] | 2(-[1,4[3,p5]]+[1,[3,4p5]])+[1,24[3,p5]] | -1234p5 + 234p51 + 124p53 + -24p531 | -[1,2[3,4p5]] | -[1,2][3,4]p5
<02><41><35> | -2[1,[3,5p]4]-2[3,5[1,p4]] | 2[1,[3,5p4]] | [1,2[3,5p]4]+2[3,5[1,p4]] | 2[1,5p[3,4]]+[1,2[3,5p]4] | 2(-[1,[3,5p]4]+[1,[3,5p4]])+[1,2[3,5p]4] | -1235p4 + 235p41 + 125p43 + -25p431 | -[1,2[3,5p4]] | -[1,2]5p[3,4]
<02><41><53> | 2[1,[3,p5]4]+2[3,[1,p4]5] | -2[1,[3,p54]] | -[1,2[3,p5]4]-2[3,[1,p4]5] | -2[1,p5[3,4]]-[1,2[3,p5]4] | 2(+[1,[3,p5]4]-[1,[3,p54]])-[1,2[3,p5]4] | 123p54 + -23p541 + -12p543 + 2p5431 | [1,2[3,p54]] | [1,2]p5[3,4]
<02><15><34> | 2[1,5[3,4p]]+2[3,4[1,5p]] | -2[1,[3,45p]] | -[1,25[3,4p]]-2[3,4[1,5p]] | -2[1,[3,45p]]-[1,2]5[3,4p] | 2(+[1,5[3,4p]]-[1,[3,45p]])-[1,25[3,4p]] | 12345p + -2345p1 + -1245p3 + 245p31 | [1,2[3,45p]] | [1,2]([3,45p]-5[3,4p])
<02><15><43> | -2[1,5[3,p4]]-2[3,[1,5p]4] | 2[1,[3,5p4]] | [1,25[3,p4]]+2[3,[1,5p]4] | 2[1,[3,5]p4]+[1,25[3,p4]] | 2(-[1,5[3,p4]]+[1,[3,5p4]])+[1,25[3,p4]] | -1235p4 + 235p41 + 125p43 + -25p431 | -[1,2[3,5p4]] | -[1,2][3,5]p4
<02><51><34> | -2[1,[3,4p]5]-2[3,4[1,p5]] | 2[1,[3,4p5]] | [1,2[3,4p]5]+2[3,4[1,p5]] | 2[1,4p[3,5]]+[1,2[3,4p]5] | 2(-[1,[3,4p]5]+[1,[3,4p5]])+[1,2[3,4p]5] | -1234p5 + 234p51 + 124p53 + -24p531 | -[1,2[3,4p5]] | -[1,2]4p[3,5]
<02><51><43> | 2[1,[3,p4]5]+2[3,[1,p5]4] | -2[1,[3,p54]] | -[1,2[3,p4]5]-2[3,[1,p5]4] | -2[1,[3,p54]]-[1,2][3,p4]5 | 2(+[1,[3,p4]5]-[1,[3,p54]])-[1,2[3,p4]5] | 123p54 + -23p541 + -12p543 + 2p5431 | [1,2[3,p54]] | [1,2]([3,p54]-[3,p4]5)
<03><12><45> | 3[1,2[4,5p]]+3[4,5[1,2p]] | -3[1,2[4,5p]] | -[1,23[4,5p]]-3[4,5[1,2p]] | -[1,23[4,5p]] |  | 12345p + -2345p1 + -1235p4 + 235p41 | [1,23[4,5p]] | 0
<03><12><54> | -3[1,2[4,p5]]-3[4,[1,2p]5] | 3[1,2[4,p5]] | [1,23[4,p5]]+3[4,[1,2p]5] | [1,23[4,p5]] |  | -1234p5 + 234p51 + 123p54 + -23p541 | -[1,23[4,p5]] | 0
<03><21><45> | -3[1,[4,5p]2]-3[4,5[1,p2]] | 3[1,[4,5p]2] | [1,3[4,5p]2]+3[4,5[1,p2]] | [1,3[4,5p]2] |  | -1345p2 + 345p21 + 135p42 + -35p421 | -[1,3[4,5p]2] | 0
<03><21><54> | 3[1,[4,p5]2]+3[4,[1,p2]5] | -3[1,[4,p5]2] | -[1,3[4,p5]2]-3[4,[1,p2]5] | -[1,3[4,p5]2] |  | 134p52 + -34p521 + -13p542 + 3p5421 | [1,3[4,p5]2] | 0
<03><14><25> | 3[1,4[2,5p]]+3[2,5[1,4p]] | -3[1,[2,45p]] | -[1,34[2,5p]]-[2,35[1,4p]] | -3[1,[2,4]5p]-[1,34[2,5p]]-[2,3]5[1,4p] | =31425p-31245p+3245p1-13425p+1345p2-345p21=3[2,45p]1+[3,1](425p-245p) no, cant reduce further? | 12345p + -2345p1 + -1345p2 + 345p21 | [1,[2,345p]] | -3[1,[2,4]5p]-[1,[34,2]5p]-[2,3]5[1,4p]
<03><14><52> | -3[1,4[2,p5]]-3[2,[1,4p]5] | 3[1,[2,4p5]] | [1,34[2,p5]]+[2,3[1,4p]5] | 3[1,[2,4]p5]+[1,34[2,p5]]+[2,3][1,4p]5 |  | -1234p5 + 234p51 + 134p52 + -34p521 | -[1,[2,34p5]] | 3[1,[2,4]p5]-[1,[2,34]p5]+[2,3][1,4p]5
<03><41><25> | -3[1,[2,5p]4]-3[2,5[1,p4]] | 3[1,[2,5p4]] | [1,3[2,5p]4]+[2,35[1,p4]] | 3[1,5p[2,4]]+[1,3[2,5p]4]+[2,3]5[1,p4] |  | -1235p4 + 235p41 + 135p42 + -35p421 | -[1,[2,35p4]] | -[1,[2,3]5]p4-[1,3]5p[2,4]
<03><41><52> | 3[1,[2,p5]4]+3[2,[1,p4]5] | -3[1,[2,p54]] | -[1,3[2,p5]4]-[2,3[1,p4]5] | -3[1,p5[2,4]]-[1,3[2,p5]4]-[2,3][1,p4]5 |  | 123p54 + -23p541 + -13p542 + 3p5421 | [1,[2,3p54]] | [1,3]p5[2,4]+[1,[2,3]p54]-[2,3][1,p4]5
<03><15><24> | 3[1,5[2,4p]]+3[2,4[1,5p]] | -3[1,[2,45p]] | -[1,35[2,4p]]-[2,34[1,5p]] | -3[1,[2,45p]]-[1,3]5[2,4p]-[2,3]4[1,5p] | -31245p+3145p2-345p21+32415p-23415p+2345p1 | 12345p + -2345p1 + -1345p2 + 345p21 | [1,[2,345p]] | [1,[2,3]4]5p+[1,3][2,45p]-[1,3]5[2,4p]
<03><15><42> | -3[1,5[2,p4]]-3[2,[1,5p]4] | 3[1,[2,5p4]] | [1,35[2,p4]]+[2,3[1,5p]4] | 3[1,[2,5]p4]+[1,35[2,p4]]+[2,3][1,5p]4 |  | -1235p4 + 235p41 + 135p42 + -35p421 | -[1,[2,35p4]] | 3[1,[2,5]p4]-[1,[2,35]p4]+[2,3][1,5p]4
<03><51><24> | -3[1,[2,4p]5]-3[2,4[1,p5]] | 3[1,[2,4p5]] | [1,3[2,4p]5]+[2,34[1,p5]] | 3[1,4p[2,5]]+[1,3[2,4p]5]+[2,3]4[1,p5] | reduces to 8 | -1234p5 + 234p51 + 134p52 + -34p521 | -[1,[2,34p5]] | -[1,3]4p[2,5]-[1,[2,3]4]p5
<03><51><42> | 3[1,[2,p4]5]+3[2,[1,p5]4] | -3[1,[2,p54]] | -[1,3[2,p4]5]-[2,3[1,p5]4] | -3[1,[2,p54]]-[1,3][2,p4]5-[2,3][1,p5]4 |  | 123p54 + -23p541 + -13p542 + 3p5421 | [1,[2,3p54]] | -3[1,[2,p54]]-[1,3][2,p4]5-[2,3][1,p5]4+[1,[2,3p54]]
<04><12><35> | 4[1,2[3,5p]]+4[3,5[1,2p]] | -4[1,2[3,5p]] | -[1,24[3,5p]]-[3,45[1,2p]] | -[1,24[3,5p]]-[3,4]5[1,2p] |  | 12345p + -2345p1 + -1245p3 + 245p31 | [1,2[3,45p]] | -[3,4]5[1,2p]+[1,2[3,4]5p]
<04><12><53> | -4[1,2[3,p5]]-4[3,[1,2p]5] | 4[1,2[3,p5]] | [1,24[3,p5]]+[3,4[1,2p]5] | [1,24[3,p5]]+[3,4][1,2p]5 |  | -1234p5 + 234p51 + 124p53 + -24p531 | -[1,2[3,4p5]] | [3,4][1,2p]5-[1,2[3,4]p5]
<04><21><35> | -4[1,[3,5p]2]-4[3,5[1,p2]] | 4[1,[3,5p]2] | [1,4[3,5p]2]+[3,45[1,p2]] | [1,4[3,5p]2]+[3,4]5[1,p2] |  | -1345p2 + 345p21 + 145p32 + -45p321 | -[1,[3,45p]2] | -[1,[3,4]5]p2
<04><21><53> | 4[1,[3,p5]2]+4[3,[1,p2]5] | -4[1,[3,p5]2] | -[1,4[3,p5]2]-[3,4[1,p2]5] | -[1,4[3,p5]2]-[3,4][1,p2]5 |  | 134p52 + -34p521 + -14p532 + 4p5321 | [1,[3,4p5]2] | -[3,4][1,p2]5+[1,[3,4]p52]
<04><13><25> | 4[1,3[2,5p]]+4[2,5[1,3p]] | -4[1,[2,35p]] | -[1,34[2,5p]]-[2,45[1,3p]] | -4[1,[2,3]5p]-[1,34[2,5p]]-[2,4]5[1,3p] | 4[1,3[2,p5]-[2,35p]] | 12345p + -2345p1 + -1345p2 + 345p21 | [1,[2,345p]] | -4[1,[2,3]5p]+[1,[2,34]5p]-[2,4]5[1,3p]
<04><13><52> | -4[1,3[2,p5]]-4[2,[1,3p]5] | 4[1,[2,3p5]] | [1,34[2,p5]]+[2,4[1,3p]5] | 4[1,[2,3]p5]+[1,34[2,p5]]+[2,4][1,3p]5 |  | -1234p5 + 234p51 + 134p52 + -34p521 | -[1,[2,34p5]] | 4[1,[2,3]p5]-[1,[2,34]p5]+[2,4][1,3p]5
<04><31><25> | -4[1,[2,5p]3]-4[2,5[1,p3]] | 4[1,[2,5p3]] | [1,4[2,5p]3]+[2,45[1,p3]] | 4[1,5p[2,3]]+[1,4[2,5p]3]+[2,4]5[1,p3] | 1425p3 - 145p23 + 2451p3 - 245p31 + 415p23 - 415p32 - 4251p3 + 45p321 somehow = -[1,4]5p[2,3]-[1,[2,4]5]p3+[1,[2,45p3]] | -1245p3 + 245p31 + 145p32 + -45p321 | -[1,[2,45p3]] | -[1,[2,4]5]p3-[1,4]5p[2,3]
<04><31><52> | 4[1,[2,p5]3]+4[2,[1,p3]5] | -4[1,[2,p53]] | -[1,4[2,p5]3]-[2,4[1,p3]5] | -4[1,p5[2,3]]-[2,4][1,p3]5-[1,4[2,p5]3] |  | 124p53 + -24p531 + -14p532 + 4p5321 | [1,[2,4p53]] | [1,4]p5[2,3]+[1,[2,4]p53]-[2,4][1,p3]5
<04><15><23> | 4[1,5[2,3p]]+4[2,3[1,5p]] | -4[1,[2,35p]] | -[1,45[2,3p]]-[2,34[1,5p]] | -[1,4]5[2,3p]+4[2,3[1,5p]]-4[1,[2,35p]]-[2,34[1,5p]] |  | 12345p + -2345p1 + -1345p2 + 345p21 | [1,[2,345p]] | -[1,4]5[2,3p]+4[2,3[1,5p]]-4[1,[2,35p]]-[2,34[1,5p]]+[1,[2,345p]]
<04><15><32> | -4[1,5[2,p3]]-4[2,[1,5p]3] | 4[1,[2,5p3]] | [1,45[2,p3]]+[2,4[1,5p]3] | 4[1,[2,5]p3]+[2,4][1,5p]3+[1,45[2,p3]] |  | -1245p3 + 245p31 + 145p32 + -45p321 | -[1,[2,45p3]] | 4[1,[2,5]p3]+[2,4][1,5p]3-[1,[2,45]p3] | =[12,345p]-4[12,35p]
<04><51><23> | -4[1,[2,3p]5]-4[2,3[1,p5]] | 4[1,[2,3p5]] | [1,4[2,3p]5]+[2,34[1,p5]] | (4[1,3p[2,5]]-4[2,3[1,p5]]+[1,4[2,3p]5])+[2,34[1,p5]] |  | -1234p5 + 234p51 + 134p52 + -34p521 | -[1,[2,34p5]] | 4[1,3p[2,5]]-4[2,3[1,p5]]+[1,4[2,3p]5]+[2,34[1,p5]]-[1,[2,34p5]]
<04><51><32> | 4[1,[2,p3]5]+4[2,[1,p5]3] | -4[1,[2,p53]] | -[1,4[2,p3]5]-[2,4[1,p5]3] | -[1,4][2,p3]5-[2,4][1,p5]3-4[1,[2,p53]] |  | 124p53 + -24p531 + -14p532 + 4p5321 | [1,[2,4p53]] | -[1,4][2,p3]5-[2,4][1,p5]3-4[1,[2,p53]]+[1,[2,4p53]]
<05><12><34> | 5[1,2[3,4p]]+5[3,4[1,2p]] | -5[1,2[3,4p]] | -[1,25[3,4p]]-[3,45[1,2p]] | 5[3,4[1,2p]]-[1,25[3,4p]]-[3,45[1,2p]] |  | 12345p + -2345p1 + -1245p3 + 245p31 | [1,2[3,45p]] | 5[3,4[1,2p]]-[1,25[3,4p]]+[1,2[3,45p]]-[3,45[1,2p]]
<05><12><43> | -5[1,2[3,p4]]-5[3,[1,2p]4] | 5[1,2[3,p4]] | [1,25[3,p4]]+[3,5[1,2p]4] | [3,5][1,2p]4+[1,25[3,p4]] |  | -1235p4 + 235p41 + 125p43 + -25p431 | -[1,2[3,5p4]] | [3,5][1,2p]4-[1,2[3,5]p4]
<05><21><34> | -5[1,[3,4p]2]-5[3,4[1,p2]] | 5[1,[3,4p]2] | [1,5[3,4p]2]+[3,45[1,p2]] | -5[3,4[1,p2]]+[1,5[3,4p]2]+[3,45[1,p2]] |  | -1345p2 + 345p21 + 145p32 + -45p321 | -[1,[3,45p]2] | -[1,[34,5]]p2+[1,[4,5]p32]-[4,5][1,p2]3
<05><21><43> | 5[1,[3,p4]2]+5[3,[1,p2]4] | -5[1,[3,p4]2] | -[1,5[3,p4]2]-[3,5[1,p2]4] | -[3,5][1,p2]4-[1,5[3,p4]2] |  | 135p42 + -35p421 + -15p432 + 5p4321 | [1,[3,5p4]2] | -[3,5][1,p2]4+[1,[3,5]p42]
<05><13><24> | 5[1,3[2,4p]]+5[2,4[1,3p]] | -5[1,[2,34p]] | -[1,35[2,4p]]-[2,45[1,3p]] | -5[1,[2,3]4p]+5[2,4[1,3p]]-[1,35[2,4p]]-[2,45[1,3p]] |  | 12345p + -2345p1 + -1345p2 + 345p21 | [1,[2,345p]] | -5[1,[2,3]4p]+5[2,4[1,3p]]-[1,35[2,4p]]-[2,45[1,3p]]+[1,[2,345p]]
<05><13><42> | -5[1,3[2,p4]]-5[2,[1,3p]4] | 5[1,[2,3p4]] | [1,35[2,p4]]+[2,5[1,3p]4] | 5[1,[2,3]p4]+[2,5][1,3p]4+[1,35[2,p4]] |  | -1235p4 + 235p41 + 135p42 + -35p421 | -[1,[2,35p4]] | 5[1,[2,3]p4]+[2,5][1,3p]4-[1,[2,35]p4]
<05><31><24> | -5[1,[2,4p]3]-5[2,4[1,p3]] | 5[1,[2,4p3]] | [1,5[2,4p]3]+[2,45[1,p3]] | (5[1,4p[2,3]]-5[2,4[1,p3]]+[1,5[2,4p]3])+[2,45[1,p3]] | reduces to 12 | -1245p3 + 245p31 + 145p32 + -45p321 | -[1,[2,45p3]] | 5[1,4p[2,3]]-5[2,4[1,p3]]+[1,5[2,4p]3]+[2,45[1,p3]]-[1,[2,45p3]]
<05><31><42> | 5[1,[2,p4]3]+5[2,[1,p3]4] | -5[1,[2,p43]] | -[1,5[2,p4]3]-[2,5[1,p3]4] | -5[1,p4[2,3]]-[2,5][1,p3]4-[1,5[2,p4]3] |  | 125p43 + -25p431 + -15p432 + 5p4321 | [1,[2,5p43]] | [1,5]p4[2,3]+[1,[2,5]p43]-[2,5][1,p3]4
<05><14><23> | 5[1,4[2,3p]]+5[2,3[1,4p]] | -5[1,[2,34p]] | -[1,45[2,3p]]-[2,35[1,4p]] | 5[1,4[2,3p]]+5[2,3[1,4p]]-5[1,[2,34p]]-[1,45[2,3p]]-[2,35[1,4p]] |  | 12345p + -2345p1 + -1345p2 + 345p21 | [1,[2,345p]] | 5[1,4[2,3p]]+5[2,3[1,4p]]-5[1,[2,34p]]-[1,45[2,3p]]-[2,35[1,4p]]+[1,[2,345p]]
<05><14><32> | -5[1,4[2,p3]]-5[2,[1,4p]3] | 5[1,[2,4p3]] | [1,45[2,p3]]+[2,5[1,4p]3] | 5[1,[2,4]p3]+[2,5][1,4p]3+[1,45[2,p3]] |  | -1245p3 + 245p31 + 145p32 + -45p321 | -[1,[2,45p3]] | 5[1,[2,4]p3]+[2,5][1,4p]3-[1,[2,45]p3]
<05><41><23> | -5[1,[2,3p]4]-5[2,3[1,p4]] | 5[1,[2,3p4]] | [1,5[2,3p]4]+[2,35[1,p4]] | (5[1,3p[2,4]]-5[2,3[1,p4]]+[1,5[2,3p]4])+[2,35[1,p4]] | reduces to 12 | -1235p4 + 235p41 + 135p42 + -35p421 | -[1,[2,35p4]] | 5[1,3p[2,4]]-5[2,3[1,p4]]+[1,5[2,3p]4]+[2,35[1,p4]]-[1,[2,35p4]]
<05><41><32> | 5[1,[2,p3]4]+5[2,[1,p4]3] | -5[1,[2,p43]] | -[1,5[2,p3]4]-[2,5[1,p4]3] | -[1,5][2,p3]4+(5[2,[1,p4]3]-5[1,[2,p43]]-[2,5[1,p4]3]) | reduces to 12 | 125p43 + -25p431 + -15p432 + 5p4321 | [1,[2,5p43]] | -[1,5][2,p3]4+[5,2][1,p4]3-5[1,[2,p43]]+[1,[2,5p43]]
Note on A2: Chaudhary, Shantanu:

## Extra Notes
Thoughts/Ideas
which terms will be able to be represented by the same tensors? | Do we need to not that before hand
What will be the check that everything is working out ?
Time dependent pauli operators
Integrals then matlab
Integrals then matlab
Idea: Write TCL 4 out using fermionic/bosonic Wick's Law

## Work Plan (hidden)
Create a Work Plan in this worksheet. The title of this worksheet is in cell C1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Towards a simplified TCL6 generator
Phase headings are in cells C2, D2, E2, and F2. There is an arrow shape in each cell with the text "Phase 1", "Phase 2", "Phase 3", and "Phase 4" in them, in addition to cell text, which is hidden behind each shape. Each phase has corresponding activities and outcomes that are listed below each heading. | Phase 1 | Phase 2 | Phase 3 | Phase 4
Titles for each phase are listed in this row from cells C3 through F3. Overwrite or delete the sample data to create your own titles. | Phase 1 Activity & Outcomes Title | Phase 2 Activity & Outcomes Title | Phase 3 Activity & Outcomes Title | Phase 4 Activity & Outcomes Title
Activities for each phase are listed in the table starting in cell C4. Column B contains the word Activity in hidden text. This helps you navigate the table with a screen reader. Some screen readers will read the text as you navigate to other rows so you don't get lost between tables in this worksheet. Sample text for each phase is in columns C4 through F4. Enter your own list of activies for each phase in the Activites table. A shape overlaps column B with the word "Activities" as a visual representation of what is contained in this table. Continue to cell A11 for the next instruction. | Meeting to discuss math prelims | Everyone tries to simplify a single term from step 1 on their own, meet and go over solutions | Biweekly meetings to discuss progress and troubleshoot any issues | List of activities
| Everyone reviews attempts to complete half solved term. | Activity 1
| Read references on Master Equations and open quantum systems | Activity 2
This row marks the end of the sample table "Activities." To add more Activities for any of the phases, simply add new rows above this one. Continue to cell A13 for the next instruction. | To add more Activities, insert new rows above this line
Titles for each Outcome for the above phases are listed in this row from cells C13 through F13. Overwrite or delete the sample data to create your own titles. | Phase 1 Outcomes Title | Phase 2 Outcomes Title | Phase 3 Outcomes Title | Phase 4 Outcomes Title
Outcomes for each phase are listed in the table starting in cell C14. Column B contains the word Outcome in hidden text. This helps you navigate the table with a screen reader. Some screen readers will read the text as you navigate to other rows so you don't get lost between tables in this worksheet. Sample text for each phase is in columns C14 through F14. Enter your own list of outcomes for each phase in the Outcomes table. A shape overlaps column B with the word "Outcomes" as a visual representation of what is contained in this table. Continue to cell A19 for the next instruction. | List of Outcomes | List of Outcomes | List of Outcomes | List of Outcomes
| Outcome 1 | Outcome 1
Outcome 2
Outcome 3
Outcome 4
This row marks the end of the sample table "Outcomes." To add more Outcomes for any of the phases, simply add new rows above this one. | To add more Outcomes, insert new rows above this line
Preliminaries
Ramp-up
Divide and Conquer
Reconviene and Recombine
Activities
Outcomes